SOFTWARE PROJECT PROPOSAL

# TradingAgents Web Platform

Customer-Facing Product & Agent Analysis Dashboard

| Client | Wang Qiang | Date | May 22, 2026 |
| --- | --- | --- | --- |
| Organization | N/A (Individual) | Budget | $6,400 USD |
| Submitted By | FineCore LLC (finecore.dev) | Timeline | 3 weeks |

Proposal Status: Discovery Phase - Ready for Implementation

Important Notice This proposal describes software delivery scope, technical implementation, and project management only. It is not financial, investment, legal, tax, or regulatory advice. Live trading, broker onboarding, and compliance obligations should be reviewed by the client and qualified advisors.

# Table of Contents

Executive Summary / Project Overview

Project Objectives

Scope of Work

Technical Approach / Solution Architecture

Technology Stack

Non-Functional Requirements (NFRs)

Team Composition & Roles

Project Timeline / Milestones

Deliverables

Assumptions & Dependencies

Risk Analysis & Mitigation Plan

Change Management Process

Communication & Reporting Plan

Testing & Quality Assurance

Deployment & Release Strategy

Maintenance & Support Plan

Cost Estimate / Pricing

Appendices

## 1. Executive Summary / Project Overview

TradingAgents is evolving from a multi-agent trading research framework into a customer-facing web platform. This proposal outlines the development of a comprehensive web application that integrates the existing tradingagents/ research framework and tradingbot/ execution/auth/broker tooling into a unified platform.

The platform will enable end-users to:

Deploy and analyze multi-agent trading strategies

Review agent reasoning and decision-making processes

Execute trades manually or delegate to broker-automated trading

Leverage token-based authentication and analysis

This 3-week engagement focuses on building the core customer-facing product platform with essential features required for MVP launch.

## 2. Project Objectives

Primary Goals:

Deliver a functional, customer-ready web platform that bridges research capabilities and live trading execution

Enable users to interact with trading agents through an intuitive interface

Provide transparency into agent reasoning for trust and auditability

Support both manual oversight and automated trading workflows

Success Metrics (TBD – subject to client prioritization):

Platform availability: [TBD]

User onboarding time to first trade: [TBD]

Agent reasoning transparency: [TBD – success criteria]

Trade execution reliability: [TBD – target SLA]

## 3. Scope of Work

### A. Functional Scope

User Modules & Features:

Authentication & Authorization

Token-based user authentication (OAuth2 / JWT)

Role-based access control (user, admin)

Secure credential storage for broker API keys

Agent Management & Deployment

Dashboard to list, deploy, and monitor trading agents

Configuration interface for agent parameters

Real-time agent status and performance metrics

Agent Reasoning & Transparency

Display agent decision logs with reasoning chains

Visualize input data, model predictions, and execution decisions

Historical audit trail for compliance and learning

Trading Execution Interface

Manual trade submission with pre-execution preview

One-click approval/rejection for agent-recommended trades

Automated execution settings and risk limits

Performance & Analytics Dashboard

Portfolio overview and P&L tracking

Agent performance metrics (win rate, Sharpe ratio, drawdown, etc.)

Trade history and execution logs

Broker Integration

Abstracted broker API layer (auth, order submission, execution)

Support for [TBD – specific brokers to be confirmed]

Real-time market data feed (if applicable)

Administration Panel

User management and account settings

System health and error monitoring

Audit logging

### B. Out of Scope (Current Phase)

Mobile application (web-only for this phase)

Advanced backtesting or strategy optimization tools

Multi-account or fund management

Machine learning model training or refinement within the platform

Regulatory compliance reporting (e.g., Form 4, insider trading disclosures)

Integration with third-party charting or analysis libraries beyond basic charting

Custom API marketplace or partner integrations

## 4. Technical Approach / Solution Architecture

### High-Level Architecture

┌─────────────────────────────────────────────────────────────┐ │ Customer Web Platform │ ├─────────────────────────────────────────────────────────────┤ │ Frontend Layer (Web UI) │ │ - React/Next.js SPA │ │ - Real-time updates (WebSockets) │ │ - Agent dashboard, trading interface, analytics │ ├─────────────────────────────────────────────────────────────┤ │ API Layer (RESTful / GraphQL) │ │ - Authentication & token management │ │ - Agent lifecycle management │ │ - Trade execution & order management │ │ - User preferences & settings │ ├─────────────────────────────────────────────────────────────┤ │ Business Logic & Integration │ │ - TradingAgents Framework (agent research & analysis) │ │ - TradingBot Execution Layer (broker auth, order routing) │ │ - Agent reasoning engine & transparency layer │ │ - Token-based analysis & metrics │ ├─────────────────────────────────────────────────────────────┤ │ Data Layer │ │ - User & authentication data │ │ - Agent configurations & execution logs │ │ - Trade history & performance metrics │ ├─────────────────────────────────────────────────────────────┤ │ External Integrations │ │ - Broker APIs (execution, account data, market data) │ │ - Market data providers (if applicable) │ └─────────────────────────────────────────────────────────────┘

### Data Flow

User logs in with token-based auth → receives JWT

User configures or selects an agent from the dashboard

Agent processes market data and generates trading signals

Agent reasoning is logged and displayed in the UI

User reviews agent recommendation and approves/rejects

Trade execution routed through TradingBot execution layer

Broker API executes order; confirmation logged and displayed

Portfolio and agent performance updated in real-time dashboard

## 5. Technology Stack

| Layer | Technology Recommendation | Notes |
| --- | --- | --- |
| Frontend | React 18 + Next.js | SSR for performance, built-in routing |
| Styling | Tailwind CSS | Rapid UI development |
| State Mgmt | Zustand / Redux | Client-side state for UI |
| Real-time | WebSocket / Socket.io | Live agent updates & trade execution |
| Backend | Node.js + Express / NestJS | TBD – language compatibility with TradingAgents/TradingBot |
| API Style | RESTful (+ GraphQL if advanced querying required) | TBD |
| Database | PostgreSQL | Relational data (users, trades, agents, audit logs) |
| Caching | Redis | Session management, real-time data |
| Hosting | AWS (EC2, RDS, ALB) | TBD – final infrastructure per client |
| Auth | JWT + OAuth2 | Token-based, broker API integration |
| Logging | ELK Stack / CloudWatch | Audit, error, and performance logs |
| Monitoring | DataDog / New Relic | TBD – APM and alerts |

Decisions TBD:

Final broker APIs to support (Interactive Brokers, Alpaca, etc.)

Market data provider (Alpha Vantage, IEX Cloud, etc.)

Advanced charting library (TradingView, Lightweight Charts, etc.)

Deployment region and multi-region strategy

## 6. Non-Functional Requirements (NFRs)

| Requirement | Target | Notes |
| --- | --- | --- |
| Performance |  |  |
| API response time | < 200ms (p95) | For dashboard queries |
| Trade execution latency | < 1s (order to confirmation) | Critical for live trading |
| Page load time | < 3s (fully interactive) | Lighthouse score: 80+ |
| Scalability |  |  |
| Concurrent users | [TBD] | Initial target vs. growth projection |
| Trade throughput | [TBD] trades/min | Peak capacity |
| Agent instances | [TBD] concurrent agents | Per user and platform-wide |
| Security |  |  |
| Authentication | OAuth2 + JWT | Token expiry: [TBD] minutes |
| Data encryption | TLS 1.3 in-transit; AES-256 at-rest | Broker credentials & PII |
| API rate limiting | [TBD] requests/min per user | DDoS / brute-force protection |
| Audit logging | 100% of user actions & trades | Immutable log for compliance |
| Password policy | [TBD] – complexity, rotation | Or SSO-only if preferred |
| Availability / Uptime |  |  |
| Platform SLA | [TBD] – 99.5% / 99.9% | Business continuity expectations |
| Graceful degradation | Agent recommendations still available if broker API fails | Manual fallback |
| Disaster recovery RTO | [TBD] hours | Data backup & restore strategy |
| Compliance |  |  |
| Data retention | [TBD] – trade & audit logs | Regulatory requirements |
| GDPR / CCPA | Compliance assessment: [TBD] | Right to deletion, data portability |
| Financial regulation | [TBD] – does platform need compliance? | Depends on client jurisdiction |

## 7. Team Composition & Roles

| Role | Responsibility | Allocation | Duration |
| --- | --- | --- | --- |
| Project Lead | Oversight, client communication, scope management | Full-time | 3 weeks |
| Full-Stack Engineer (2) | Frontend (React/Next.js), backend API, integration | Full-time each | 3 weeks |
| Backend/Integration Engineer | TradingAgents/TradingBot integration, broker API setup, data layer | Full-time | 3 weeks |
| Frontend/UI Engineer | Dashboard UI, agent reasoning visualization, UX polish | Full-time | 3 weeks |
| QA / Testing | Unit, integration, UAT, performance testing | Full-time | Final 1.5 weeks |
| DevOps/Infra | CI/CD, hosting setup, security hardening, monitoring | Part-time | As-needed |

Total Resource Commitment: ~3.5 FTE over 3 weeks

## 8. Project Timeline / Milestones

| Phase | Duration | Deliverables |
| --- | --- | --- |
| Week 1: Core Infra & API | 5 days | Backend scaffolding, auth system, agent API endpoints, database schema, CI/CD pipeline, broker API integration skeleton |
| Week 2: Frontend & Integration | 5 days | React dashboard UI, agent management interface, trading execution UI, WebSocket real-time updates, TradingAgents/TradingBot integration, reasoning log display |
| Week 3: Polish, Testing & Launch | 5 days | End-to-end testing, performance optimization, security hardening, bug fixes, deployment to staging, UAT with client, go-live |

Key Milestones:

Day 3: Backend API contract frozen, frontend scaffolding complete

Day 7: Core agent management & authentication working, broker API connected

Day 10: MVP dashboard functional, trades executable end-to-end

Day 12: QA sign-off, performance benchmarks met

Day 15: Production deployment, client cutover

## 9. Deliverables

Code & Documentation:

Full source code repository (GitHub/GitLab)

Frontend (React/Next.js)

Backend API (Node.js/NestJS)

TradingAgents & TradingBot integration layer

Infrastructure as Code (Terraform / CloudFormation)

Technical documentation

API specification (OpenAPI/Swagger)

Architecture & design decisions

Deployment runbook

Troubleshooting guide

User documentation

Getting started guide

Agent configuration manual

Trading interface walkthrough

FAQ & support contact info

Deployed Application:

Staging environment (live, accessible to client for UAT)

Production environment (fully operational on launch date)

Post-Launch Support:

Initial 1-week free support window for critical bugs

Knowledge transfer session with client team (1-2 hours)

## 10. Assumptions & Dependencies

Client Responsibilities:

Provide access to broker API credentials and documentation

Confirm list of supported brokers for this phase

Provide any existing TradingAgents framework code or model weights

Confirm data sources for real-time market data

Designate a primary contact for sign-offs and decisions

External Dependencies:

Broker API availability and rate limits

Market data provider (if real-time data required)

Any third-party libraries or SDKs required by TradingAgents/TradingBot

DNS, SSL certificates, and hosting infrastructure readiness

Technical Assumptions:

TradingAgents and TradingBot frameworks are mature and stable

Broker APIs support standard authentication (OAuth2 or API key)

No major schema or breaking changes to existing frameworks mid-project

Initial user base < 1,000 concurrent users (can scale post-launch)

Project Assumptions:

3-week timeline assumes clear scope and minimal revisions

Budget of $6,400 covers development labor and basic infrastructure; client covers hosting after go-live

Client will conduct UAT in final week; sign-off required before production deployment

Post-launch maintenance and feature development are out of scope for this proposal

## 11. Risk Analysis & Mitigation Plan

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Broker API Integration Delays | Timeline slip, trade execution blocked | Medium | Start broker API integration in Week 1; maintain fallback to manual API calls if needed; pre-stage test accounts early |
| Unclear Agent Reasoning Requirements | Feature rework, scope creep, delivery delay | Medium | Schedule kickoff call to define reasoning transparency requirements (visualization, format, data depth); document in writing |
| TradingAgents/TradingBot Framework Issues | Blocked integration, rework required | Low-Medium | Conduct pre-project framework audit; maintain open channel with framework maintainers; keep fallback manual execution path |
| Scope Creep | Budget overrun, timeline slip | High | Strict change control process; document out-of-scope items in writing; weekly scope reviews with client |
| Performance Under Load | User experience degradation, reputation risk | Medium | Load testing in Week 2; real-time data with WebSockets to reduce polling; Redis caching for agent data; optimize API queries |
| Security Vulnerabilities | Data breach, credential exposure, compliance violation | Medium-High | OWASP Top 10 review; code security scanning (SonarQube, Snyk); third-party security audit before go-live; secrets management best practices |
| Insufficient UAT Window | Bugs in production, customer dissatisfaction | Medium | Reserve 3-4 days in Week 3 for UAT; provide sandbox environment early for client testing; prioritize critical path testing |

## 12. Change Management Process

Change Request Workflow:

Client submits change request in writing with description, business rationale, and impact estimate

Project lead assesses impact on timeline, budget, and scope

Impact assessment communicated to client within 24 hours

If approved: scope updated, timeline adjusted, cost impact (if any) negotiated

No change can proceed without written approval

Change Approval Authority:

Changes ≤ 4 hours: Project lead can approve

Changes 4–16 hours: FineCore CTO approval required

Changes > 16 hours or affecting timeline: Client and FineCore mutual sign-off required

Out-of-Scope Feature Requests:

Features not in original scope → added to a Post-Launch Roadmap

Client can prioritize these for Phase 2 (subject to separate proposal)

## 13. Communication & Reporting Plan

Meetings:

Daily Standup: 15 min, 9 AM (async Slack updates acceptable if time zones prevent sync)

Weekly Sync: 30 min Thursdays, progress update + blockers + next week preview

Sprint Retrospective: 30 min Friday end of Week 2 & Week 3

Reporting:

Weekly Report: Email summary of completed work, upcoming tasks, risks, metrics

Burndown Chart: Updated daily on shared dashboard (GitHub Projects / Jira)

Blockers & Issues: Escalated immediately if blocking team

Tools:

Code: GitHub / GitLab (with branch protection & pull request reviews)

Project Tracking: Jira / Linear / GitHub Projects

Chat: Slack #tradingagents-platform channel

Video Calls: Google Meet / Zoom

Documentation: Shared Notion / Confluence space or GitHub Wiki

## 14. Testing & Quality Assurance

Testing Strategy:

| Test Type | Scope | Timeline | Owner |
| --- | --- | --- | --- |
| Unit Tests | Core business logic, utility functions | Ongoing (Week 1–2) | Engineers |
| Integration Tests | API ↔ Database, TradingAgents integration, broker API mock | Week 2 | Backend team |
| API Contract Tests | Frontend ↔ Backend contract validation | Week 2 | Full-stack team |
| End-to-End (E2E) | User workflows: login → agent config → trade execution | Week 3 | QA + engineers |
| Load & Performance | 100+ concurrent users, trade throughput | Week 2–3 | QA + DevOps |
| Security | SQL injection, XSS, CSRF, credential exposure; OWASP Top 10 | Week 3 | Security review + QA |
| UAT | Client validation against requirements | Week 3 (Thu–Fri) | Client + QA |

Acceptance Criteria (per user story):

All unit tests passing (target: >80% code coverage)

API response times within NFR targets

Zero critical/high security findings

All UAT sign-off tasks completed

Tools:

Jest / Mocha (unit tests)

Cypress / Playwright (E2E tests)

k6 / JMeter (load testing)

OWASP ZAP / Burp Suite (security scanning)

GitHub Actions / CircleCI (CI/CD automated testing)

## 15. Deployment & Release Strategy

Environments:

Local Development – Each engineer's machine

Staging – Pre-production replica; available for client UAT

Production – Live customer environment

Deployment Pipeline:

Git Commit → CI/CD Tests → Build → Deploy to Staging → Client UAT → Approval → Deploy to Production

Rollout Strategy:

Initial Launch: Full cutover to production on Day 15

Monitoring: Real-time dashboards during first 24 hours post-launch

Quick Fix Protocol: If critical bug emerges, hotfix deployed within 2 hours

Versioning:

Semantic versioning: v1.0.0 for production launch

Patch versions (v1.0.1) for bug fixes

Minor versions (v1.1.0) for new features (post-launch)

Rollback Strategy:

Previous version snapshot maintained on standby

Database backup before each production deployment

If critical issue detected: rollback to previous version within 30 minutes

Root cause analysis & fix before re-deploy

## 16. Maintenance & Support Plan

Post-Launch Support (Included in Proposal):

Duration: 1 week (Days 15–21, May 22–28)

Scope: Critical bug fixes, deployment troubleshooting

Response Time: 2 hours for critical issues (trading blocked), 8 hours for medium issues

Support Channel: Slack #support, escalation to project lead

Ongoing Maintenance (Phase 2 – Out of Scope):

Security patch management

Dependency updates

Database backups & monitoring

Infrastructure scaling as user base grows

Minor bug fixes & feature requests

Suggested Support Tiers (for future):

Tier 1 (Basic): Email support, 24-hour response time

Tier 2 (Professional): Priority support, 4-hour response, quarterly health checks

Tier 3 (Premium): Dedicated account manager, 1-hour response, monthly strategy calls

## 17. Cost Estimate / Pricing

Budget Allocation:

| Component | Cost | Notes |
| --- | --- | --- |
| Development Labor | $5,000 | ~3.5 FTE × 3 weeks @ $450/day blended rate |
| Infrastructure & Hosting (3 weeks) | $600 | AWS EC2, RDS, ALB staging + production |
| Third-Party Tools & Licenses | $400 | GitHub Actions, monitoring, security scanning, Jira |
| Testing & QA Tools | $200 | Load testing, security scanning (if not free tier) |
| Contingency (5%) | $320 | Buffer for unknowns |
| TOTAL | $6,400 | Fixed cost for 3-week development phase |

Payment Schedule:

50% ($3,200) upfront upon contract signing

50% ($3,200) upon production deployment & UAT sign-off

What's Included:

✓ Full-stack development & integration

✓ Testing & QA (unit, integration, E2E, security)

✓ 1-week post-launch support for critical bugs

✓ Technical documentation & API specs

✓ Deployment & infrastructure setup

What's NOT Included:

✗ Ongoing maintenance beyond 1-week support window

✗ Additional feature development or customization

✗ Compliance certifications (SOC 2, ISO 27001, etc.)

✗ Broker account setup or funding

✗ Market data provider subscription (client responsibility)

Optional Add-Ons (TBD – separate quote if needed):

Mobile app (iOS/Android) – estimated +$12,000–15,000

Advanced backtesting & optimization tools – estimated +$4,000–6,000

Multi-broker or portfolio management features – estimated +$3,000–5,000

Regulatory compliance modules – estimated +$5,000–10,000

## 18. Appendices

### A. Glossary

Agent: An autonomous algorithm that analyzes market data and generates trading recommendations

Reasoning Log: Timestamped record of the data inputs, processing steps, and decision rationale for each trade

TradingAgents: Multi-agent research framework for developing, testing, and analyzing trading strategies

TradingBot: Execution layer handling authentication, order routing, and live trade execution via broker APIs

Token-Based Analysis: Quantitative metrics and reporting on agent performance, risk, and compliance

Broker API: RESTful interface to broker services (order execution, account data, market data)

### B. Sample Agent Reasoning Display (Concept)

Agent: "Momentum Scout" Timestamp: 2026-05-22 14:35:00 UTC Input Data: - Last 20 candles (1H interval): [OHLCV data] - RSI (14): 72.5 (overbought) - MA20: $45,123.50, MA50: $44,987.25 (bullish crossover) - Volume: 150M shares (above 20-day avg) Decision Logic: 1. RSI > 70? YES → Strong momentum signal 2. MA20 > MA50? YES → Uptrend confirmed 3. Volume above average? YES → Conviction high 4. Portfolio risk limit exceeded? NO → Safe to trade 5. Recommendation: BUY 0.5 BTC @ market price Confidence Score: 82% Execution: APPROVED by user on 2026-05-22 14:35:15 UTC Order: BTC-USD market order filled @ $45,150 (0.5 BTC) Status: EXECUTED

### C. Broker API Integration Checklist

☐ Authentication method confirmed (OAuth2 / API Key / both)

☐ Sandbox account provisioned for testing

☐ API documentation reviewed & endpoint list compiled

☐ Rate limits & throttling policy documented

☐ Error handling & retry logic designed

☐ Order types supported: market, limit, stop-loss, trailing stop (confirm scope)

☐ Account data retrieval: positions, balances, trade history (confirm scope)

☐ Real-time market data feeds: prices, quotes, depth (confirm scope)

☐ Webhook / notification mechanism for order fills (if available)

### D. Pre-Project Kickoff Checklist

Before Week 1 starts:

☐ Client access credentials collected (broker sandbox, any internal systems)

☐ TradingAgents/TradingBot code repositories accessible to team

☐ Project team assigned and onboarded

☐ Development, staging, and production environments provisioned

☐ CI/CD pipeline scaffolded

☐ Slack, Jira, and documentation spaces created

☐ First standup scheduled

☐ Change management & communication expectations documented

### E. Success Criteria (Client Acceptance)

Functional:

✓ User can authenticate and access dashboard

✓ Agent management (create, deploy, monitor) fully functional

✓ Agent reasoning displayed with full decision audit trail

✓ Manual trade submission & broker execution working

✓ Portfolio & agent performance metrics visible and accurate

✓ All broker API integrations live (confirmed list)

Performance:

✓ API response times meet NFR targets (< 200ms p95)

✓ Page load time < 3 seconds

✓ Trade execution confirmed within 1 second

✓ Zero critical security findings in final audit

Quality:

✓ Unit test coverage > 80%

✓ All E2E tests passing

✓ Zero critical/high bugs in UAT

✓ Load testing completed (meets concurrent user target)

## Sign-Off

Proposed by: FineCore LLC

Date: May 22, 2026

Valid through: May 29, 2026 (7 days)

To proceed, please confirm:

Project scope and objectives align with your vision

Budget ($6,400) and timeline (3 weeks) are acceptable

Client team can dedicate time for weekly syncs, UAT, and sign-offs

Any TBD items above require clarification before start date

Next Steps:

Sign contract & return to FineCore LLC

Provide broker API access details & credentials (secure channel)

Schedule project kickoff meeting for Week 1 start

Confirm any TBD items identified above

Questions? Contact: [TBD – project lead contact info]

This proposal is confidential and intended solely for the named client. Reproduction or distribution without written consent is prohibited.